## Gantt Chart
ByteStore Project II - Gantt Chart
Edit the Start Date and End Date columns below - Duration and the chart update automatically.
Phase | Start Date | End Date | Duration (days)
Requirement Analysis & Literature Review | 2026-09-14 | 2026-10-11 | 28
System Design (ER, Use Case, Flow Chart) | 2026-09-28 | 2026-11-01 | 35
Core Integration / DB Schema Extension | 2026-10-26 | 2026-11-29 | 35
Collaborative & Content-Based Filtering Module | 2026-11-23 | 2027-01-17 | 56
Testing & Integration | 2027-01-19 | 2027-02-08 | 21
Documentation & Final Report Writing | 2026-10-12 | 2027-02-14 | 126
Submission & Evaluation | 2027-02-16 | 2027-02-16 | 1